## Sheet1
TicketID | Status | Subject
QAT-28 | Resolved | Framework Set Up for Set Up Team to create a single/few Entity In Multiple Hotels
QAT-29 | Resolved | Create Users in Multiple Hotel
QAT-30 | Resolved | Delete Users from Multiple Hotels
QAT-31 | Resolved | Save Source Of Business in Multiple Hotels
QAT-32 | Resolved | Save Departments in Multiple Hotels
QAT-33 | Resolved | Add Room Taxes in Multiple Hotels
QAT-34 | Resolved | Save PayTypes in Multiple Hotels
QAT-36 | Resolved | Refresh Allotments in Multiple Hotels
QAT-38 | Resolved | Framework Set Up to Automate Channel Manager Test Cases
QAT-46 | Resolved | To Create multiple Slab taxes in Multiple Hotels
QAT-47 | Resolved | To Edit multiple Slab taxes in Multiple Hotels
QAT-48 | New | Sync Packages to Channel Mangers from Admin Console
QAT-35 | New | Save AddOns in Multiple Hotels
QAT-49 | InProgress | Logs for Assistance of Manual Team

## Logs
Date | Logs
2017-07-04 | EditSlabTax Completed Added 4 new Test Cases Channel Smoke Identified 21 New Test Cases for Channel Functional Test Cases of Allotments Discussion with Team regarding GST and New Issues
2017-07-05 | Automated 1 Test Cases:CaptureAllotment_TC_17 Modified Test Cases Script :pushbooking_TC_18